## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : GAU GAS DISTRIBUTION AND BILLING AUTOMATION
| DATE : |  | VINAY KIRAN M | VINAY BHAT |  | TILAK K | PERUMAL S
MILESTONE 1 : LEARNING ARDUINO PROGRAMMING
| 19 - 09 - 2016 |  | Introduction to Arduino Board | Introduction to Bluetooth Module |  | Introduction to GSM module | Introduction to HTML
| 20 - 09 - 2016 |  | Arduino pins and connections | Exploring Bluetooth module |  | Learning behaviour of GSM module | Exploring HTML and CSS
| 21 - 09 - 2016 |  |  | HC-05 pins and connections |  | Working on GSM modules | Hands on using basic HTML tags
22 - 09 - 2016
| 23 - 09 - 2016 |  | ENGINEERS DAY AND DEVELOTHON
24 - 09 - 2016
| 25 - 09 - 2016 |  | SUNDAY
| 26 - 09 - 2016 |  | Exploring Arduino IDE | AT commands |  | GSM module | HTML,CSS,PHP
27 - 09 - 2016
| 28 - 09 - 2016 |  | Basic projects on Arduino | Sending data between HC-05 and mobile
29 - 09 - 2016
| 30 - 09 - 2016 |  | Connecting Arduino with HC-05 bluetooth module |  |  |  | JavaScript
1 - 10 - 2016
| 2 - 10 - 2016 | INTERNALS
3 - 10 - 2016
4 - 10 - 2016
5 - 10 - 2016
6 - 10 - 2016
7 - 10 - 2016
8 - 10 - 2016
| 9 - 10 - 2016 |  | SUNDAY
| 10 - 10 - 2016 |  | DUSSERA HOLIDAYS
11 - 10 - 2016
12 - 10 - 2016
13 - 10 - 2016
14 - 10 - 2016
15 - 10 - 2016
16 - 10 - 2016
| 17 - 10 - 2016 |  | preparing SRS document | workbreak down structure |  | Abstract | Agile methodology implementation
18 - 10 - 2016
| 19 - 10 - 2016 |  | Meeting about the Gau Gas
| 20 - 10 - 2016 |  | AMCAT assessment | AMCAT assessment |  | AMCAT assessment | Meet with the guide
| 21 - 10 - 2016 |  | Open Source India Event | Open Source India Event |  | Open Source India Event | Open Source India Event
| 22 - 10 - 2016 |  | Verifying document with guide | Verifying document with guide |  | Verifying document with guide | Verifying document with guide
| 23 - 10 - 2016 |  | Analysing current method implemented | Exploring the product |  | Exploring gateways | comminucation with arduino
24 - 10 - 2016
| 25 - 10 - 2016 |  |  |  |  | Introduction to Java
| 26 - 10 - 2016 |  | XML parsing , PHP | Introduction to esp wifi module 8266 |  |  | GET and POST method analysis using JSON
27 - 10 - 2016
28 - 10 - 2016
| 29 - 10 - 2016 |  | SUNDAY
| 30 - 10 - 2016 |  | Android Application development | Working on esp module |  | Learning the concepts of JDBC .. | Design of Dashboard
31 - 10 - 2016
2016-11-01
| 2016-11-02 |  |  | MySQL, xampp servers
| 2016-11-03 |  |  |  |  | connecting database to website's
2016-11-04
| 2016-11-05 |  |  | working on xampp servers , creating databases and operations on database..
2016-11-06
2016-11-07
| 2016-11-08 |  | INTERNALS
2016-11-09
2016-11-10
2016-11-11
2016-11-12
2016-11-13
2016-11-14
2016-11-15
2016-11-16
| 2016-11-17 |  | Android Application development | Encryption and Decryption Algorithm |  | SMS API to Send and receive Data | Getting data from database and displaying
2016-11-18
2016-11-19
2016-11-20
2016-11-21
2016-11-22
2016-11-23
2016-11-24
2016-11-25
2016-11-26
2016-11-27
| 2016-11-28 |  | Externals
2016-11-29
2016-11-30
2016-12-01
2016-12-02
2016-12-03
2016-12-04
2016-12-05
2016-12-06
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07
2017-01-08
2017-01-09
2017-01-10
2017-01-11
2017-01-12
| 2017-01-13 |  | MILESTONE 2:INTEGRATION
2017-01-14
2017-01-15
| 2017-01-16 |  | SUNDAY
| 2017-01-17 |  | Integrating Arduino with HC-05 and GSM module |  |  |  | Implementing SMS API in application
2017-01-18
2017-01-19
2017-01-20
2017-01-21
| 2017-01-22 |  | Intial hardware setup and testing |  |  | learning android studio | database design
2017-01-23
2017-01-24
2017-01-25
2017-01-26
2017-01-27
2017-01-28
2017-01-29
2017-01-30
| 2017-01-31 |  | Integrating Arduino with current sensor |  |  | Desiging Android app which receives text message | Implementing database and testing
2017-02-01
2017-02-02
2017-02-03
2017-02-04
2017-02-05
| 2017-02-06 |  | Integrating gsm module with arduino and sending some dummy text messages |  |  | receving the messages and storing in database
2017-02-07
2017-02-08
2017-02-09
| 2017-02-10 |  |  |  |  | designing and testing android app which read the inbox
2017-02-11
2017-02-12
2017-02-13
| 2017-02-14 |  | sending usage logs through text messages along with authentication key |  |  | receving the messages from gsm and storing in database through app
2017-02-15
2017-02-16
| 2017-02-17 |  |  |  |  | parsing text message and verifying the user in database
2017-02-18
| 2017-02-19 |  |  |  | Sunday
2017-02-20
2017-02-21
| 2017-02-22 |  | Documentation
2017-02-23
2017-02-24
2017-02-25
2017-02-26
semester holidays
Sunday
placements
Maha Shivaratri
Review
Sunday