## Sheet1
JYOTHY INSTITUTE OF TECHNOLOGY
PROJECT WORK BREAK DOWN STRUTCTURE
PROJECT TITLE : GAU GAS DISTRIBUTION AND BILLING AUTOMATION
| DATE : |  | VINAY KIRAN M | VINAY BHAT | TILAK K | PERUMAL S
MILESTONE 1 : LEARNING ARDUINO PROGRAMMING
| 19 - 09 - 2016 |  | Introduction to Arduino Board | Introduction to Arduino Board | Introduction to Arduino Board | Introduction to Arduino Board
| 20 - 09 - 2016 |  | Signals : Analog & Digital | Signals : Analog & Digital | Signals : Analog & Digital | Signals : Analog & Digital
| 21 - 09 - 2016 |  | Arduino Pin Modes & Connections | Arduino Pin Modes & Connections | Arduino Pin Modes & Connections | Arduino Pin Modes & Connections
| 22 - 09 - 2016 |  | Small Example Projects Provided By Arduino Website | Small Example Projects Provided By Arduino Website | Small Example Projects Provided By Arduino Website | Small Example Projects Provided By Arduino Website
| 23 - 09 - 2016 |  | For Loop usage in Arduino | For Loop usage in Arduino | For Loop usage in Arduino | For Loop usage in Arduino
| 24 - 09 - 2016 |  | Working with IR sensor & Temperature Sensor | Working with IR sensor & Temperature Sensor | Working with IR sensor & Temperature Sensor | Working with IR sensor & Temperature Sensor
| 25 - 09 - 2016 |  | SUNDAY
| 26 - 09 - 2016 |  | Ultrasonic Sensor | Ultrasonic Sensor | Ultrasonic Sensor | Ultrasonic Sensor
| 27 - 09 - 2016 |  | Special Study About Wifi And bluetooth Sensors that can be used with the arduino board | Special Study About Wifi And bluetooth Sensors that can be used with the arduino board | Special Study About Wifi And bluetooth Sensors that can be used with the arduino board | Special Study About Wifi And bluetooth Sensors that can be used with the arduino board
MILESTONE 2 : CLOUD COMPUTING
| 28 - 09 - 2016 |  | Introduction to Cloud Computing | Introduction to Cloud Computing | Introduction to Cloud Computing | Introduction to Cloud Computing
29 - 09 - 2016
| 30 - 09 - 2016 |  | Sending and Receiving Messages Through Arduino Borad Using The Wifi Module ESP8266 | Sending and Receiving Messages Through Arduino Borad Using The Wifi Module ESP8266 | Sending and Receiving Messages Through Arduino Borad Using The Wifi Module ESP8266 | Sending and Receiving Messages Through Arduino Borad Using The Wifi Module ESP8266
1 - 10 - 2016
| 2 - 10 - 2016 | INTERNAL'S
3 - 10 - 2016
4 - 10 - 2016
5 - 10 - 2016
6 - 10 - 2016
7 - 10 - 2016
8 - 10 - 2016
9 - 10 - 2016
10 - 10 - 2016
11 - 10 - 2016
12 - 10 - 2016
13 - 10 - 2016
14 - 10 - 2016
15 - 10 - 2016
16 - 10 - 2016
17 - 10 - 2016
18 - 10 - 2016
19 - 10 - 2016
20 - 10 - 2016
21 - 10 - 2016
22 - 10 - 2016
23 - 10 - 2016
24 - 10 - 2016
25 - 10 - 2016
26 - 10 - 2016
27 - 10 - 2016
28 - 10 - 2016
29 - 10 - 2016
30 - 10 - 2016
31 - 10 - 2016